## Sheet1
Issue | Title | Fix By | ETA | Detail | Created by Day
YATU
BUG | UNABLE TO REGISTER | Lian | 2022-01-22 |  | 2022-01-15
BUG | Video keep growing when coming back from other pages | Gao xiang | 2022-01-22 |  | 2022-01-15
Question | Do we need to add audio explicitly? | Gao xiang | 2022-01-16 | Old code has to explicitly add audio tag. If you do not want video? | 2022-01-15
Change request | Student board is text area until specifically requested | Lian | 2022-01-21 | Currently we post code to formatted whiteboard. We should simply post to student exercise board so that the can pick ip up and modify. White board (formatted) is only good for showing old sample code. | 2022-01-20
New Function | Sync board | Lian | 2022-01-22 | Use a timer to sync every 3 seconds | 2022-01-15
New Function | Sync student boards | Lian | 2022-01-29 |  | 2022-01-15
New Function | Auto Sync | Lian | 2022-02-05 | Automatically check content of student and teacher and sync if difference found | 2022-01-15
New Function | Schedule a class: server | Lian |  | DB Time table: open class time slot, define class length and frequency | 2022-01-29 | class table
| Schedule a class: client | Lian |  | Call API: Get available class time for a subject |  | sjct, class length: 1(2) hrs, how many classes (4 ~ 10), instances: begin, end time, rooms left
New Function | Save home work
New Function | Paypqal API (Client) | Gao xiang |  | Paypal UI / Script /
New Function | Paypqal API (Server) | Li li |  | Paypal Service API / Connector /DB
New Function | Research: how to run Java Code at the service | Li Li |  | We need to have Java code run at the server in a sandbox securely. Please come up with a plan on how to do it. | 2022-02-05
finMind
TASK | ADD ERROR PAGE (MESSAGES)
Fix wizard term-perm option
From application to pipeline

## schema
Teacher time | ==> | class instance | group | subject | class instance member
date |  | id |  |  | id
begin |  | group id | id | teacher | userid
end |  | begin |  |  | status: paid
class sizes |  | end
|  | sbj id |  | id