## Sheet1
Issue | Title | Fix By | ETA | Detail | Created by Day | Status | Remarks
YATU
BUG | UNABLE TO REGISTER | Lian | 2022-01-22 |  | 2022-01-15 | 100%
BUG | Video keep growing when coming back from other pages | Gao xiang | 2022-01-22 |  | 2022-01-15
Question | Do we need to add audio explicitly? | Gao xiang | 2022-01-16 | Old code has to explicitly add audio tag. If you do not want video? | 2022-01-15
Bug | Student arrival event never sent hence no student cosole displayed | Lian |  |  | 0%
Change request | Student board is text area until specifically requested | Lian | 2022-01-21 | Currently we post code to formatted whiteboard. We should simply post to student exercise board so that the can pick ip up and modify. White board (formatted) is only good for showing old sample code. | 2022-01-20 | 100%
Task 1 | Sync board | Lian | 2022-01-22 | Use a timer to sync every 5 seconds | 2022-01-15 | 99% | Need to sync with students who has partial content. Task 2
Task 2 | Sync with each student | lian | 2022-01-23 | USE a timer to sync every 10 seconds to check hash of the content an to make sure we are in sync |  | 80% (need to test)
Task 3 | Sync student boards | Lian | 2022-01-29 | During exercise, obtain student board content on deman | 2022-01-15 | 100%
Task 4 | Schedule a class: server | Lian |  | DB Time table: open class time slot, define class length and frequency | 2022-01-29 | 0% |  | class table
Task 5 | Schedule a class: client | Lian |  | Call API: Get available class time for a subject |  | 0% |  | sjct, class length: 1(2) hrs, how many classes (4 ~ 10), instances: begin, end time, rooms left
Task 6 | Save home work |  |  |  |  | 0%
Task 7 | Paypqal API (Client) | Gao xiang |  | Paypal UI / Script /
Task 8 | Paypqal API (Server) | Li li |  | Paypal Service API / Connector /DB
Task 9 | Research: how to run Java Code at the service | Li Li |  | We need to have Java code run at the server in a sandbox securely. Please come up with a plan on how to do it. | 2022-02-05
Task 10 | Add student name tag on top of student cosole | Lian |  | Add a name tag to identify student. Especially useful when multiple students are present | 2022-01-25 | 100%
Task 11 | Sync to teacher's mode when joining the class | Lian |  | Now we set the exercise mode, but this not desirable since we don't know which mode to switch to if a student is late | 2022-02-06 | 0%
Issue 1 | User Name should be w/o special chars since we use it as video id | Lian |  |  |  | 0%
Issue 2 | Timer not working every time | Lian
ADD ERROR PAGE (MESSAGES)
From application to pipeline

## schema
Teacher time | ==> | class instance | group | subject | class instance member
date |  | id |  |  | id
begin |  | group id | id | teacher | userid
end |  | begin |  |  | status: paid
class sizes |  | end
|  | sbj id |  | id